## ResourceOwners
Resource | Primary Owner (Suggested) | Approver(s) | Notes
Windows Build Host (execution environment) | JM | Security (hardening); Infrastructure | Runs ingestion, embedding, generation, validation, and packaging jobs.
Service Account / Identity | Cloud | Security / Risk | Non-interactive identity for file share, DB, and provider access.
Secrets Storage (keys, DB creds) | JM/Cloud? | Security / Risk | Central secrets handling (Credential Manager/Key Vault/pipeline secrets).
File Share Corpus (PowerShell library) | JM | Endpoint Engineering leadership | Defines blessed content and include/exclude boundaries for RAG.
Ingestion Script + Schedule (Invoke_RAGIngestion) | JM | Endpoint Engineering lead | Code asset that produces chunks.jsonl/docs.jsonl/state.json.
Embedding Provider (Embeddings) | JM | Security / Risk; Cloud governance | Provision embedding endpoint, quotas, network access.
PostgreSQL + pgvector (Vector Store) | JM/Cloud | Security (DB access); Infrastructure | Owns backups/patching; pivot point to Azure AI Search if needed.
Embedding Write Pipeline (chunks → vectors → pgvector) | JM | Endpoint Engineering lead; DB lead | Proof-of-viability glue that upserts embeddings and metadata.
Retrieval Module (Top-K context bundle) | JM | Endpoint Engineering lead | Determines retrieval quality; central to RAG success.
LLM Provider (generation) | Collab/Jose | Security / Risk | Provision generation model access; orchestration owns prompts.
Generation Orchestrator (prompt→spec→scripts) | JM | Endpoint Engineering lead | Produces spec JSON + install/uninstall scripts + commands.
Spec Schema + JSON Enforcement Rules | JM | Endpoint Engineering lead | Defines non-negotiable naming/command rules and constraints.
Preflight Validator (PreflightJSONValidator...) | JM | Endpoint Engineering lead | Go/No-Go gate enforcing schema/policy before packaging.
Packaging Tooling (IntuneWinAppUtil + staging) | JM | Endpoint Engineering lead | Controls clean Source/Output layout and packaging execution.
Intune Dev Tenant / Pilot Ring | JM | Change Control; Endpoint Engineering lead | Owns test rings, assignments, deployment monitoring.
Diagnostics + Runbooks | JM | Endpoint Ops lead | Troubleshooting playbooks, log collection, escalation patterns.

## DP-AP Task Owners
TaskID | TaskName | Workstream | Primary Owner (Suggested) | Contributors | Approver(s) | Code Required | Deliverable | FromResource | ToResource | Owner (Named) | Status | TargetDate | Notes
DP-01 | Grant SMB read access | Data Plane / Indexing | IAM / Identity Team | File Share Owner; Endpoint Engineering | Security / Risk | No | File share ACL updated to grant SMB read access to the service account; access test captured (e.g., successful directory listing). | Service Account & Permissions | File Share Corpus
DP-02 | Grant DB role + privileges | Data Plane / Indexing | Database Platform Team | IAM / Identity Team; Endpoint Automation Engineer | Security (DB access); Infrastructure | No | PostgreSQL role/user created and granted required privileges for RAG tables; connectivity + SELECT/INSERT validation recorded. | Service Account & Permissions | PostgreSQL + pgvector
DP-03 | Schedule ingestion job | Data Plane / Indexing | Platform Engineering / Windows Server Team | DevOps; Endpoint Automation Engineer | Infrastructure | No | Scheduled task/job created on the build host to run ingestion; last-run status = success; ingestion log retained. | Windows Build Host | Ingestion (chunks.jsonl)
DP-04 | Read corpus files | Data Plane / Indexing | Endpoint Engineering (Content Owner) | File Share Owner | Endpoint Engineering Lead | No | Ingestion run confirms corpus traversal (file count summary) with zero access errors; ingestion log retained. | File Share Corpus | Ingestion (chunks.jsonl)
DP-05 | Produce chunks.jsonl | Data Plane / Indexing | Endpoint Automation Engineer | Endpoint Engineering (Content Owner) | Endpoint Engineering Lead | Yes | Ingestion output artifacts produced: chunks.jsonl, docs.jsonl, state.json; sample chunk validated for correctness. | Ingestion (chunks.jsonl) | Embedding Write
DP-06 | Call embeddings API | Data Plane / Indexing | Endpoint Automation Engineer | Cloud/AI Platform Team; DevOps | Security / Risk | Yes | Embedding provider reachable and authenticated; embedding batches succeed; embedding-write logs show successful calls. | Embedding Provider | Embedding Write
DP-07 | Connect + ensure schema | Data Plane / Indexing | Database Platform Team | Endpoint Automation Engineer | Security (DB access) | No | pgvector extension enabled; rag_chunks table/schema present; verification queries succeed; optional vector index created. | PostgreSQL + pgvector | Embedding Write
AP-01 | Generate query embedding | App Plane | Endpoint Automation Engineer | Cloud/AI Platform Team | Security / Risk | Yes | Query-embedding function/script implemented; test prompt returns embedding vector of expected dimension. | Embedding Provider | Retrieval Module
AP-02 | Run similarity search | App Plane | Endpoint Automation Engineer | Database Platform Team | Endpoint Engineering Lead | Yes | Similarity search query/script implemented; returns Top-K chunk IDs with scores/distances; filtered retrieval validated. | PostgreSQL + pgvector | Retrieval Module
AP-03 | Assemble context bundle | App Plane | Endpoint Automation Engineer | Endpoint Engineering (Content Owner) | Endpoint Engineering Lead | Yes | Context bundle builder produces consolidated Top-K context payload (ordered + token-limited) ready for LLM prompts. | Retrieval Module | Generation Orchestrator
AP-04 | Generate spec + scripts | App Plane | Endpoint Automation Engineer | App Packaging Engineers | Endpoint Engineering Lead | Yes | Spec JSON generated and passes preflight validation; install/uninstall scripts generated with required versioned naming + commands. | Generation Orchestrator | Preflight Validator
AP-05 | Enforce gates / approve | App Plane | Endpoint Engineering (Quality Gate Owner) | Endpoint Automation Engineer | Endpoint Engineering Lead | Yes | Preflight validator integrated as a gate; pass/fail report emitted; packaging is blocked on validation failure. | Preflight Validator | Packaging
AP-06 | Run packaging job | App Plane | Endpoint Packaging Team | Platform Engineering / Windows Server Team | Endpoint Engineering Lead | No | .intunewin produced in output folder using IntuneWinAppUtil; packaging logs captured; artifact name/version verified. | Windows Build Host | Packaging
AP-07 | Deploy to test ring | App Plane | Intune/MEM Admin Team | Endpoint Packaging Team; Endpoint Ops | Change Control | No | Deployment executed in Intune dev/pilot ring; install success evidence captured (status report + diagnostics/IME logs as needed). | Packaging | Intune Dev/Pilot Testing