## Sheet1
TaskID | TaskName | Workstream | FromResource | ToResource | Deliverable | Code Required | Owner | Status | TargetDate | Notes
DP-01 | Grant SMB read access | Data Plane / Indexing | Service Account & Permissions | File Share Corpus | File share ACL updated to grant SMB read access to the service account; access test captured (e.g., successful directory listing). | No
DP-02 | Grant DB role + privileges | Data Plane / Indexing | Service Account & Permissions | PostgreSQL + pgvector | PostgreSQL role/user created and granted required privileges for RAG tables; connectivity + SELECT/INSERT validation recorded. | No
DP-03 | Schedule ingestion job | Data Plane / Indexing | Windows Build Host | Ingestion (chunks.jsonl) | Scheduled task/job created on the build host to run ingestion; last-run status = success; ingestion log retained. | No
DP-04 | Read corpus files | Data Plane / Indexing | File Share Corpus | Ingestion (chunks.jsonl) | Ingestion run confirms corpus traversal (file count summary) with zero access errors; ingestion log retained. | No
DP-05 | Produce chunks.jsonl | Data Plane / Indexing | Ingestion (chunks.jsonl) | Embedding Write | Ingestion output artifacts produced: chunks.jsonl, docs.jsonl, state.json; sample chunk validated for correctness. | Yes
DP-06 | Call embeddings API | Data Plane / Indexing | Embedding Provider | Embedding Write | Embedding provider reachable and authenticated; embedding batches succeed; embedding-write logs show successful calls. | Yes
DP-07 | Connect + ensure schema | Data Plane / Indexing | PostgreSQL + pgvector | Embedding Write | pgvector extension enabled; rag_chunks table/schema present; verification queries succeed; optional vector index created. | No
AP-01 | Generate query embedding | App Plane | Embedding Provider | Retrieval Module | Query-embedding function/script implemented; test prompt returns embedding vector of expected dimension. | Yes
AP-02 | Run similarity search | App Plane | PostgreSQL + pgvector | Retrieval Module | Similarity search query/script implemented; returns Top-K chunk IDs with scores/distances; filtered retrieval validated. | Yes
AP-03 | Assemble context bundle | App Plane | Retrieval Module | Generation Orchestrator | Context bundle builder produces consolidated Top-K context payload (ordered + token-limited) ready for LLM prompts. | Yes
AP-04 | Generate spec + scripts | App Plane | Generation Orchestrator | Preflight Validator | Spec JSON generated and passes preflight validation; install/uninstall scripts generated with required versioned naming + commands. | Yes
AP-05 | Enforce gates / approve | App Plane | Preflight Validator | Packaging | Preflight validator integrated as a gate; pass/fail report emitted; packaging is blocked on validation failure. | Yes
AP-06 | Run packaging job | App Plane | Windows Build Host | Packaging | .intunewin produced in output folder using IntuneWinAppUtil; packaging logs captured; artifact name/version verified. | No
AP-07 | Deploy to test ring | App Plane | Packaging | Intune Dev/Pilot Testing | Deployment executed in Intune dev/pilot ring; install success evidence captured (status report + diagnostics/IME logs as needed). | No